Purpose of the Situational Analysis

The situational analysis aimed to explore contextual challenges, facilitators, and resources that could be leveraged to support LTC homes to implement a palliative program (SPA-LTC) in British Columbia. The purpose of this document is to serve as a guideline for other provinces/sites as they conduct their situational analyses.

Overview of Situational Analysis

Situational Analysis Experience

Scaling Up a Palliative Approach to Care in LTC Homes Across British Columbia

416 emails sent to various stakeholders in BC, including nurses, physicians, administrators, external consultants, and allied health professionals to complete the stakeholder survey

  - 34 contacts were personalized key contacts or email groups/lists representing the LTC sector among all BC health authorities

- Emails/stakeholder survey invites were also sent via newsletters, membership lists, professional development networking, and social media posting

- From the initial email campaign, 13 participant responses provided key connections to other membership lists, newsletters, social media postings, and links to local champions

- One email reminder was sent one month after the initial email contact

- Stakeholders were also specifically recruited from underrepresented geographic areas

- In total, 84 completed surveys were collected

Email Distribution

| Email Type | Number of Emails |
| --- | --- |
| Individual Emails | 416 (includes 34 key contacts) |
| BC Hospice Palliative Care Association Newsletter | 1800 |
| BC Hospice Palliative Care Association Membership List | 150 |
| North Okanagan Hospice Society Newsletter | 1793 |
| EngAge BC Membership List | 450 |
| Total Emails | 4609 |

Visual Representation of Situational Analysis

Engaging and Networking with LTC Homes

- Approaching Province Wide Leaders: Reaching out to leaders outside health authorities who have positions of influence in LTC, such as those within BC-CPC and the BC Care Providers Association.

- Engaging Health Authority Leaders: Approaching health authority staff at the Clinical Nurse Specialist and Educator levels to achieve buy-in and support for project information and survey dissemination. Also sharing information on

“what’s in it for them.”

- Fostering Relationships: Ensuring that a positive working relationship is built

over time by maintaining a consistent stream of communication (and following

up when necessary) with each private LTC home that expressed interest for

project participation.

Lessons Learned

- Leveraging Current Professional Networks

This can provide key connections to stakeholders

who may be able to further introduce you to other

networks of interest.

- Accessing Established Email Lists

This can save the time and energy of individually researching and sending emails while expanding the number of people reached.

- Researching New Networks and Key Stakeholders:

This provides the opportunity to learn about key contacts and organizations who may be valuable to the situational analysis, while allowing you to form new networks.

- Calling Key Stakeholders for Buy-In

This allows you to introduce yourself first-hand to achieve

buy-in while potentially gaining access to additional membership/email lists.